## Readings
QSCP Hamilton Inspection Department
Site: Hamilton Plant
Data Sheet
No.: QSCP-TRK-ATU100-2025 ¦ Status: Issued ¦ Date: 2025-03-28
Corrective Action Tracker - ATU-100 2024 Findings
Administrative Data
Document ID: QSCP-TRK-ATU100-2025
Date: 2025-03-28
Site: Hamilton Plant
Unit: ATU-100
Author: Jennifer Walsh, Inspection Coordinator (API 570)
Open Nonconformances and Remediation Status
QSCP-NCR-2024-031: Line 4-RA-101-06 measured at 3.6 mm. Value is below t-min of 3.81 mm. Action: Re-measure Aug 2025; replace during Aug 2026 turnaround per QSCP-IP-ATU100 Rev 4.
QSCP-NCR-2024-032: Line 2-RF-102 CMLs -04 through -07 measured below t-min of 2.16 mm. Observed metal loss of 0.9 mm since 2019. Action: Re-measure Nov 2025 (12-month interval); replace per QSCP-IP-ATU100 Rev 4.
Updated Inspection Schedule (RBI)
Line 6-RA-103-11: Next thickness measurement scheduled Feb 2026.
Line 2-RF-102: Next thickness measurement scheduled Nov 2025.
Line 4-RA-101: Next thickness measurement scheduled Aug 2025.
Reference: QSCP-IP-ATU100 Rev 4 (Piping Inspection Plan - ATU-100 (RBI)).
Sign-off | Name | Function | Date | Signature
Prepared | Jennifer Walsh | Inspection Coordinator, API 570 inspector | 2025-03-28 | ______________